## About
Tableau Blueprint Planner
Tableau Blueprint is a step-by-step methodology to becoming a data-driven organization. It assists you with deploying and operating Tableau by developing three core capabilities: agility, proficiency, and community. The Blueprint Planner will guide you through key decision points during the deployment process. Each tab is color-coded to help you identify the corresponding area. For more detailed information, visit Tableau Blueprint documentation at https://onlinehelp.tableau.com/current/blueprint/en-us/bp_overview.htm. (Updated 5/1/2020)

## Analytics Strategy
Analytics Strategy
To define your analytics strategy, you should start with your organization's vision statement and strategic initiatives, KPIs/metrics, and desired outcomes. By linking these initiatives to data and analytics, you can use them as a driver of change. Next, establish your Tableau-specific goals. Suitable metrics—especially for measuring behavioral changes—will vary for each organization, and should be evaluated at regular intervals as analytics practices evolve. Finally, document any challenges or risks to the process. Reference the Analytics Strategy and Executive Advocacy and Project Team topics for more information.
Vision Statement for the Use of Data & Analytics in Your Organization
Strategic Initiatives | Description | KPIs/Metrics/Outcomes | Timeframe/Due Date
Tableau Business Goals | Description | KPIs/Metrics/Outcomes | Timeframe/Due Date
Challenges or Risks | Description | Mitigating Factors

## Roles and Responsibilities
Roles and Responsibilities
Executive sponsors working with the project team need to consider not only how to scale the technology, but the adequate support, training, and management structure to effectively navigate change management alongside adoption, overcoming the organizational roadblocks to become a data-driven enterprise. Maximizing analytics investments and capitalizing on the transformative potential of data means that everyone encountering it—regardless skill levels and data fluency—must be able to turn insights into opportunities or innovations. In the table below, identify members of the cross-functional team who are responsible for understanding current/future state capabilities, challenges, and goals, set the vision for next 18 months with project scope, prioritization, success measures, hold regular meetings, gather/respond to feedback, and document value. Reference the Executive Advocacy and Project Team topics for more information.
Executive Roles | Responsibilities | Team Members
Executive Sponsor | The Executive Sponsor sets the vision for modern analytics, aligns projects to transformational initiatives, nominates staff for advocacy roles, and ensures accountability.
IT Sponsor | The IT Sponsor is responsible for Tableau installation, configuration, and maintenance, partners with business leaders and SMEs, enables secure, governed data access, and transitions content authoring to business users.
Analytics Sponsor | The Analytics Sponsor implements the vision for modern analytics, ensures the availability of data and content, establishes education plans and learning paths by organizational job functions, and facilitates communication throughout the user community, and aggregates business value achieved.
Line-of-Business Sponsors | Line-of-Business sponsors advocate for data-driven decision making within their respective teams, promote content authoring and governed access, encourage collaboration and sharing, and document business value.
Project Team Roles | Responsibilities | Team Members
Analytics Director | The Analytics Director owns the analytics program, including placement and fit of analytics use cases within the organization and alignment with strategic initiatives.
Enterprise Architect | The Enterprise Architect identifies technical requirements and integrates Tableau with enterprise architecture standards.
Network Administrator | The Network Administrator maintains network communications and connectivity.
Security Administrator | The Security Administrator ensures the company complies with its internal policies and external regulatory requirements, establishes and administers the overall strategies and procedures for the information security function, and evaluates risk and promotes information security awareness.
Database Administrator | The Database Administrator is responsible for the administration, monitoring, maintenance, and security of databases in the organization. The DBA will assist with modeling, structuring, and optimizing sources of data that connect to Tableau.
Systems Administrator | The Systems Administrator installs, configures, manages, and maintains the Tableau deployment in the data center or in the cloud, while enforcing company policies in compliance with business and technology strategy.
Desktop Administrator | The Desktop Administrator installs and configures client software including database drivers, Tableau Desktop, Tableau Prep, and Tableau Mobile.
Mobile Administrator | The Mobile Administrator manages mobile devices and connectivity, including company-owned and bring your own devices (BYOD).
Project Manager | The Project Manager ensures that the project is delivered on time and within budget by ensuring the project is effectively staffed, managing relationships with a wide range of groups, allocating and utilizing resources in an efficient manner, and maintaining a cooperative, motivated and successful team.
Community Leader | The Community Leader coordinates efforts related to user enablement, including support resources, engagement events, connecting users within your company, and analytics evangelism. Note: Not all organizations will have a dedicated position for these responsibilities.
Tableau Administrator Roles | Responsibilities | Team Members
Tableau Server Administrator | The Server Administrator has full access to Tableau Server configuration settings, all sites on the server, users and groups, and all content assets, such as projects, data sources (including connection information), and workbooks to monitor and maintain overall server health.
Tableau Site Administrators | Tableau Site Administrators create and manage the site’s users and groups, create projects to organize content on the site, and assign permissions to allow users (groups) to access the content. They also promote and certify content and measure the use of analytics within their site. This role applies to Tableau Server and Tableau Online.
Tableau Creator Roles | Responsibilities | Team Members
Data Steward | Data Stewards have an understanding of the business domain and the interaction of business processes with analytics. A Data Steward ensures that there are documented procedures and guidelines for data access and use and will work with Database Administrator and/or Data Engineers to plan and execute an enterprise-wide data governance, control and compliance policy.
Content Authors | Content Authors create and publish dashboards and data sources. They will also be a resource for others ramping up their Tableau skills.

## Ent. Architecture Survey - TS
Enterprise Architecture Survey - Tableau Server
As you are planning your deployment, the IT team should document the current enterprise architecture by completing the Enterprise Architecture Survey. Because Tableau is integrated with hardware, network, databases, and applications, understanding how all these things interoperate is key for installation and configuration and ongoing platform operations. Reference the Deployment topics for more information.
Area | Questions | Responses
Deployment Type/Hardware Platform | Where will you deploy - on-premises or public cloud?
What are your enterprise standard build/specs? (cores, VM, RAM)
What is your enterprise server operating system?
High Availability/Disaster Recovery | Is Tableau Server mission-critical, requiring high availability?
What is the recovery time objective (RTO)?
What is the recovery point objective (RPO)?
Security | What is your enterprise authentication protocol? (Active Directory, LDAP, SAML)
What is your security policy for service accounts related to Tableau Server?
Network | Is SSL required?
What is your policy on gateway ports over http/https?
Are there any port restrictions?
Is internet access from servers permitted?
Will users access the server externally?
Operations | What are your enterprise hardware and software management tools? (server, client, mobile)
What are your enterprise monitoring tools? (SCOM, Splunk, etc.)
How many environments do you require for servers? (Dev, UAT, Prod)
What processes exist for backup/restore?
Licensing | What is the license type (role-based subscription, core, embedded)?
Will you distribute client software keys or utilize Login Based License Management to manage license keys?
How are license assets allocated?
How will additional licensing purchases be made?
Is there a chargeback model?
Client Software | How is client software deployed - Tableau Desktop and Prep Builder? (manual, silent, self-service)
How is client software upgraded - Tableau Desktop and Prep Builder? (manual, silent, self-service)
Mobile | Who is the audience for mobile analytics, and what are the primary user scenarios?
Where will people be when they need data? (In office, the field, a home office)
How will users reach the Tableau Server if they aren’t on the same network?
Will users need to access data offline, without connecting to the internet or your network?
Will people use company-owned devices, personal devices (BYOD), or both?
What mobile device types (phone, tablet) do you support?
What mobile OS’s do you support?
How sensitive is the data?
Analytics Services | Will you be integrating external services (R Server, Python, MATLAB, WMS)?
Automation & Extensibility | What are the requirements for automation, customization? (APIs needed)
Data | What database technologies (on-premises and cloud) are sources of data?
What applications (on-premises and cloud) are sources of data?
What file-based sources of data will be used? (network folder access)
What security policies exist for database service accounts, user accounts?
What are your classifications for data security? (secret, confidential, internal, public, etc.)
Do you have any data that is restricted to a geographic region?
Are there external and/or government regulations to comply with?
Are there row-level security requirements?

## Ent. Architecture Survey - TOL
Enterprise Architecture Survey - Tableau Online
As you are planning your deployment, the IT team should document the current enterprise architecture by completing the Enterprise Architecture Survey. Because Tableau is integrated with hardware, network, databases, and applications, understanding how all these things interoperate is key for installation and configuration and ongoing platform operations. Reference the Deployment topics for more information.
Area | Questions | Responses
Security | What is your preferred authentication protocol? (SAML, Google, TableauID)
Do you leverage a cloud SSO provider (Azure AD, AD FS, OneLogin, PingOne, Okta, Salesforce)?
How do you perform user and group provisioning? (Cloud SSO, REST API, Manual)
What is your security policy for service accounts? (data sources, Tableau Bridge)
Network | Is SSL required for data source connections? (Tableau Online uses SSL by default)
What is your policy on gateway ports over http/https?
Are there any port restrictions?
Is Internet access from internal servers permitted?
Licensing | Will you distribute client software keys or utilize Login Based License Management to manage license keys?
How are license assets allocated?
How will additional licensing purchases be made?
Is there a charge-back model?
Client Software | How is client software deployed - Desktop, Prep Builder? (manual, silent, self-service)
How will client software be updated? (manual, silent, self-service)
How will Tableau Bridge be deployed and managed? (If needed, centralized recommended)
Cloud Application Integration | What are the requirements for branding and customization?
What are the requirements for automation with APIs?
What are your site monitoring needs? (trust.tableau.com, site status admin views, custom reporting in Admin Insights)
Mobile | What is your Mobile Device Management solution?
Who is the audience for mobile analytics, and what are the primary user scenarios?
Where will people be when they need data? In the field, a home office, or both?
Will users need to access data offline, without connecting to the internet or your network?
Will people use company-owned devices, personal devices (BYOD), or both?
What mobile device types (phone, tablet) do you support?
What mobile OS’s do you support?
Data | What cloud sources of data will be accessed?
What on-prem sources of data will be accessed? (databases, Virtual Private Environments, applications, files)?
Will Tableau Bridge be used to move data into Tableau Online?
What security policies exist for database service accounts, user account?
Will credentials be embedded? Will the credentials be a service account or a data steward account?
What data security measures, considerations and/or company policies are required by your organization for your internal data?
Are there external and/or government regulations to comply with?
Do you have any data that is required to be stored in a geographic region (sales territories, geographic data housing restrictions, etc.)?
Are there row-level security requirements?

## Data and Analytics Survey
Data & Analytics Survey
Before the deployment of Tableau software, each Line-of-Business Sponsor should survey their departments/teams to help them prioritize sources of data and training needs. Each business team who will be using Tableau should complete the Data and Analytics Survey or work with an IT team member to facilitate documentation of the information. The purpose of the survey is to identify sources of data that are important to their job functions, prioritize which of these data sources will be certified and available at launch, and plan end user training needs. After teams complete this information, you will use it to prioritize and categorize the published data sources. Reference the Analytics Strategy topics for more information.
Division:
Department:
Team:
Process | Question | Response
Team | What is the team's business function?
What is the targeted number of users?
Within the team is there a data engineering function?
Does your team have data access today for what needs to be analyzed?
Selection & Management | What business problems/questions need to be solved/answered?
What are the key sources of data for the team?
How does your team source data? (data warehouse, file exports, third-party)
How often does the data change?
Security | How is data secured?
Will row-level security or personalization for each user be needed?
Distribution (Current State) | How is data distributed?
How frequently is data distributed?
What formats are used?
Who prepares reports for distribution?
Who are the recipients?
Consumption (Current State) | How is data used in context of recipient's job/role?
How is data consumed? New or existing datasets?
Do consumers export and perform additional manipulation in context of your team?
From where is data accessed? (office, remote, field, etc.)
Skills | What analytical skills and capabilities exist within the team?
What analytical skills and capabilities need to be developed?
Who will be identified and trained as the Tableau Champion(s) within the team?

## Use Cases and Data Sources
Use Cases and Data Sources
To identify initial use cases, you will use the information gathered in the Data and Analytics Survey from every participating team to discover and prioritize which sources of data will be most impactful by audience. If you are just getting started or transitioning from a traditional top-down approach driven by IT to governed self-service, it is advantageous for IT or a centralized BI team to build the initial use cases across departments, including trusted data sources and dashboards. Reference the Analytics Strategy topics for more information.
Expected Audience
Data Source/Source of Data | Description | Department | Data Steward/Owner Name | Launch Date | Creators | Explorers | Viewers | Total
[7 empty] | Total | 0
Note on G4: Michael Hetrick: Use the expected audience size to prioritize published data sources and measure user engagement.
Note on J5: Michael Hetrick: Informs server capacity planning

## Data and Content Governance
Data and Content Governance
In Tableau, you govern two things: data and content. Different kinds of data and content require different kinds of governance. Your governance models combine people, process, and technology and creates accountability and enables, rather than restricts, access to secure and trusted data and for all skill levels in your organization. This makes governance a shared responsibility. Acknowledging that varying degrees of governance are required, these principles can be right-sized and applied to any kind of data regardless of where it falls in the governance spectrum. Like other Tableau platform management activities, an agile, iterative approach is needed to adapt to the evolving requirements as user adoption and engagement increase. To help you define your organization’s standards, policies, and procedures, you should complete the matrix below by answering the questions listed below. Document details such as who is responsible, what processes are needed to support it, and when it occurs. Reference the Governance topics for more information.
Governance Model
Data Governance | Description | Centralized | Delegated | Self-Governing
Data Source Management | What are the key sources of data for a department or team?
Who is the Data Steward or owner of the data?
Will you connect live or extract the data?
Should the data source be embedded or published?
Do variants of a dataset exist? If so, can they be consolidated as an authoritative source?
If multiple data sources are consolidated, does the single data source performance or utility suffer by attempting to fulfill too many use cases at once?
What business questions need to be answered by the data source?
What naming conventions are used for Published Data Sources?
Data Quality | What processes exist for ensuring accuracy, completeness, reliability, and relevance?
Have you developed a checklist to operationalize the process?
Who needs to review data prior to it becoming shared and trusted?
Is your process adaptable to business users and are they able to partner with data owners to report issues?
Enrichment & Preparation | Will data enrichment and preparation be centralized or self-service?
What organizational roles perform data enrichment and preparation?
What ETL tools and processes should be used to automate enrichment and/or preparation?
What sources of data provide valuable context when combined with each other?
How complex are the data sources to be combined?
Will users be able to use Tableau Prep Builder and/or Tableau Desktop to combine datasets?
Have standardized join or blend fields been established by the DBA to enable users to enrich and prepare datasets?
How will you enable self-service data preparation?
Data Security | How do you classify different types of data according to its sensitivity?
How does someone request access to data?
Will you use a service account or database security to connect to data?
What is the appropriate approach to secure data according to sensitivity classification?
Does your data security meet legal, compliance, and regulatory requirements?
Metadata Management | What is the process for curating data sources?
Has the data source been sized to the analysis at hand?
What is your organizational standard for naming conventions and field formatting?
Does the Tableau Data Model meet all criteria for curation, including user-friendly naming conventions?
Has the metadata checklist been defined, published, and integrated into the validation, promotion, and certification processes?
Monitoring & Management | Are schedules available for the times needed for extract refreshes?
How is raw data ingestion monitored from source systems? Did the jobs complete successfully?
Are there duplicate sources of data?
When are extract refreshes scheduled to run? How long do extracts run? Did the refresh succeed or fail?
Are subscription schedules available after extract refreshes have occurred?
Are data sources being used? By whom? How does this compare with the expected audience size?
What is the process to remove stale Published Data Sources?
Governance Model
Content Governance | Description | Centralized | Delegated | Self-Governing
Content Management | Will workbooks and data sources be shared across the company?
Will sites be used to isolate sensitive content or departments?
Will projects use an organizational (departments/teams), functional (topics), or hybrid approach?
Have sandbox and production projects been setup to support ad-hoc and validated content?
Are content naming conventions used?
Are authors publishing multiple copies of the same workbook with different filters selected?
Does content have a description, tags, and comply with visual styles?
Do you have a load time expectation and an exception procedure in place?
After employees leave the company, what is the process to reassign content ownership?
Authorization | What is the minimum site role for Active Directory/LDAP group synchronization?
Have you set all permissions for the All Users group in the Default project to None?
Are any explicit restrictions (Deny permissions) needed on the All Users group to propagate to every user account?
Have you created groups that correspond to a set of authoring and viewing capabilities for each project?
Have you reviewed effective permissions on select users to test your permissions model?
Have you locked permissions at the parent project to maintain security throughout the project hierarchy?
Have service account usernames/passwords been established for Published Data Sources?
Content Validation | Who is involved in the validation process?
Is the workbook accurate, complete, reliable, relevant, and recent?
Does the new content replace existing content?
Are the underlying data and calculations correct?
Does the workbook reflect corporate branding?
Does the workbook have a logical layout?
Are all axes and numbers formatted correctly?
Do dashboards load within the acceptable performance time?
Do filters and dashboard actions behave on the targeted views?
Does the dashboard remain useful in edge case behaviors (filtered to all, none, one value, etc.)?
Content Promotion | Who is involved in the promotion process?
Do content-promoting roles have a checklist of criteria to evaluate?
Have you clearly delineated between certified content and ad-hoc content by projects?
Is the process agile to support iterations and innovation?
Do you have workflows to address both direct and restricted sources of data and workbooks?
Content Certification | Who is responsible for designating certified content?
Have all criteria for achieving certification status been met?
Are all fields completed: about, certification notes, tags?
Content Utilization | How much traffic goes to each view?
What is the definition of stale content? How often is stale content purged?
How much indirect utilization (alerts & subscriptions) occurs?
Are subscriptions delivered on time?
Does the actual audience size match with expectations?
Does content follow a weekly, monthly, quarterly trend?
What is the frequency of login or days since last login by user cohort?
What is the distribution of workbook and data source size?

## Education Role Mapping
Education Role Mapping
Each organizational role or job function has a relationship to data that you should identify and map to Tableau roles. Assessing the skills required to operate Tableau in each organizational role requires an understanding of which tasks can be completed with each product, plus an understanding of how those products correlate to Tableau’s licenses that are detailed above. Enter your job titles that correspond to each of the Education Roles below and/or customize to fit your requirements.
Education Role | Description | Job Titles
Executive Sponsor | Executive Sponsors are responsible for driving the decisions and strategies that enable their organization’s continued growth and success. They understand market pressures, what it takes to stay competitive, and how to lead their organization forward. These leaders recognize, embrace, and promote the importance of implementing a data-driven culture to gain competitive advantage and understand the power of Tableau to achieve that goal. License types vary for Executive Sponsors based on where they are most active in their business.
Community Leader | Community Leaders are responsible for coordinating efforts related to user enablement around communications, engagement, and support. Most Community Leaders also fall into a role with heavy product usage, and will require a Creator subscription to understand how others are using Tableau.
Consumer | Consumers use data to make more informed decisions for their lines of business. They can range from administrative assistants to C-suite executives, but they share a goal of making better, more informed business decisions based on dashboards and reports others in their organization produce.
Author | Authors have a strong understanding of their market and business objectives, and they recognize the importance of making data-driven decisions. They leverage their foundational Tableau skills to make smarter business decisions more quickly by digging into their available data sources to create visualizations and dashboards mostly for their own consumption. Authors likely have a Creator license, but may also author on the web with an Explorer license.
Designer | Designers create visualizations and dashboards that help stakeholders across their organization absorb information quickly and easily. They leverage Tableau to deliver beautiful, functional, and impactful dashboards. They draw on their appreciation of the art of visual design as a clear communication tool and on their understanding of the impact that clear and engaging visualizations can have on both internal and external audiences.
Analyst | Analysts are responsible for supporting their lines of business to deliver valuable insights from data. Analysts work with complex data sources, use advanced calculations to customize data, and use advanced features (parameters, sets, filters, and forecasting) to build a range of charts and to analyze a variety of data types. Analysts perform ad-hoc analysis to help explore new data questions, produce well-designed interactive dashboards that present data accurately, and create and share data insights within their organizations for the purpose of guiding business decisions and outcomes.
Data Steward | Data Stewards understand the business domain and the interaction of business processes with analytics. Data Stewards ensure there are documented procedures and guidelines for data access and use and work with Database Administrators and/or Data Engineers to plan and execute an enterprise-wide data governance, control and compliance policy. Within Tableau, they work to curate and manage certified data sources with set user permissions in accordance with enterprise governance policies.
Data Scientist | Data Scientists are experts at deriving valuable insights for large and varied data sets. They are adept at tackling big data, know how to apply advanced analytic capabilities to answer business questions, are often domain experts, and work collaboratively across the business and IT to deliver ROI from data. They can reduce data cleansing and preparation time in Tableau Prep Builder, use Tableau Desktop for exploratory analysis, and develop final dashboards to support and clearly present project findings.
Developer | Developers translate the needs of the business into the software tools, applications, and automated processes that keep their organizations lean, smart, and efficient. They leverage Tableau to create new data products, embed visualizations and dashboards into current solutions, improve analysis processes, and integrate organizational insights into other external platforms and portals.
Site Administrator | Site Administrators manage, monitor, and maintain sites on Tableau Server or Tableau Online. They manage site organization, content publishing, groups, users, and permissions. Through their monitoring efforts, they know the latest details on site utilization, adoption, performance, and compliance. Site Administrators are key to the adoption of Tableau Server or Tableau Online in their organizations.
Server Administrator | Server Administrators ensure that their installation of Tableau Server runs smoothly. Key elements include securing the server, managing licenses, managing users, monitoring and troubleshooting server issues, and performing server maintenance. Server Administrators work tirelessly to ensure that Tableau Server is not only operational but meets the ongoing needs of the enterprise.
Server Architect | Server Architects plan Tableau Server deployments and ensure their success. Key success factors include integrating the deployment with preferred authentication options, monitoring server, and scaling server overtime to meet enterprise demand. Once implementation is complete, server architects maintain the deployment and help to investigate and resolve server issues.

## Tableau Users
Tableau Users
Identify users in each department and their license level, site role, and learning path. If your license counts are high, define user personas to classify different types of users using the education role mapping approach. Designate at least 1 champion per department. Reference the Analytics Strategy and Education topics for more information.
Name | Department | License Level | Site Role | Education Role | Onboard Date | Champion? | Creator | Server Administrator Creator
[7 empty] | Explorer | Site Administrator Creator
[7 empty] | Viewer | Site Administrator Explorer
Creator
Explorer (can publish)
Explorer
Viewer
Read-only
Unlicensed

## Community
Community
When you deploy Tableau broadly across your organization, establishing internal communications, user enablement resources, engagement activities, and support methods will promote adoption to scale data and analytics more efficiently. Reference the Communications, Engagement, and Support topics for moe information.
Communications | Description | Assigned To | Due Date
Getting Started | Connects new users with necessary resources on your intranet and throughout the company
FAQ | Easily answer common questions, as well as save time by not having to directly respond to every question
Support Options | Define where a user should go for assistance, including peer-to-peer assistance, office hours, and logging a support ticket
Announcements | Communicate everything from user group meetings, learning plans, training opportunities, and office hours to maintenance windows, upgrades, and other service-impacting events
User Directory | Make people discoverable, promotes the exchange of ideas, helps users find others in or outside of their team for assistance
Governance Models | Help your users understand the centralized, delegated, and self-governing models of data and content governance
Data Platforms | Document the database name, table or view, type of authentication, and access request requirements on each one
Certified Data | Publish what trusted data is available and help users more quickly find a governed dataset for their analysis, create a certified data source directory
Analytics Best Practices | Share guidelines for choosing the right chart type and creating effective, actionable dashboards for content consumers
Visual Style Guide | Give your users a head start on design, as well as guidance on how to differentiate between ad-hoc and certified content, which fonts and brand colors to use, and other formatting options
Events Calendar | Build an events calendar based on the organization's engagement activities
Learning Plans | Share learning plans for each of the roles
Training Videos | Curate on-demand training videos to educate users
Company Education Calendar | Schedule company training session for web-based or classroom learning
User Group Recordings | Record your internal user group meetings and make them available to anyone who was unable to attend in-person
Analytics Blog/Newsletter | Publish an analytics blog to showcase achievements and provide awareness and recognition of how data and analytics are used within your organization
Discussion Forums & Chat | Provide users with information in real time and create your own knowledge base
Engagement | Description | Assigned To | Due Date
Internal User Group | Organize your users to promote collaboration and sharing across teams
Internal Champions Group | Encourage leadership and evangelism by gathering perspectives from your Tableau Champions
Internal Admin Group | Exchange ideas, share challenges, and identify how changes will be communicated from Tableau admins
Lunch & Learn | Schedule a monthly, lunchtime meeting where people can eat, listen, and learn
Viz Games | Issue a visualization challenge and score participants on their work
Tableau Day/Analytics Day | Raise the visibility and use of data and analytics within your company
Support | Description | Assigned To | Due Date
User Support Process | Enable your user community to request more support beyond the self-help resources established above
Champion Development | Prioritize and invest in developing their skills prior to beginning a company-wide, education initiative and support their continued learning
Skills Pyramid | Develop user skills at all levels and encourage progression to the next
Mentoring | Enable more experienced Tableau users to share their knowledge with others

## Upgrade Planning
Upgrade Planning
When you deploy Tableau broadly across your organization, establishing internal communications, user enablement resources, engagement activities, and support methods will promote adoption to scale data and analytics more efficiently. Reference the Communications, Engagement, and Support topics for more information.
Area | Questions | Notes
Guiding Principles | How often will upgrades occur?
How will the upgrade version be selected?
How will the new version impact existing solutions?
Upgrade Plan | What IT roles will be involved in the upgrade?
Do you have a single production instance of Tableau or multiple production instances of Tableau to be upgraded?
Do you have a test environment setup that matches the production environment specs and configuration?
Will your configuration be changing to support high-availability? If already HA, are all processes redundant?
Do you have a disaster recovery environment setup?
Are backups taken daily and stored outside of the production Tableau Server?
Are you changing to role-based licensing?
What are the current and new Tableau Server/Tableau Online and Tableau Desktop versions?
What are the current and new Tableau Prep Builder versions?
What are the current and new Tableau Mobile versions?
What are the current and new Resource Monitoring Tool versions?
What are the current and new tabcmd, Tableau Bridge, or Content Migration Tool versions, if installed on individual computers?
Are there any programmatic dependencies that will be impacted by the upgrade? (embedded analytics, portal development, automation with APIs)
Will additional capacity be needed to support new workloads between this upgrade and the next upgrade? (extract refreshes, flow execution, subscriptions)
Will additional capacity be needed to support estimated number of new users between this upgrade and the next upgrade?
Are there any planned platform changes to the completed after the upgrade? (OS, hypervisor, hardware, or cloud provider)
What is the rollback plan in case there are issues with the upgrade?
Communication Plan | What are the business goals for the upgrade?
What new features or functionality will be available in the new version?
How will users be notified of the pending upgrade?
How will users be notified after the upgrade is completed?
How will users install new client and mobile software? (silent, self-service, manual)
Education Plan | How are users educated on new features or functionality?
What Tableau-provided resources will be added to the enablement intranet?
What company-specific resources need to be created?
Will Lunch & Learn sessions or on-demand videos be created?
Support Plan | What self-help resources are available?
What categories exist for post-upgrade support requests?
How are support requests triaged?
What is the escalation path for post-upgrade incidents?

## Upgrade Process Checklist
Upgrade Process Checklist
Before you upgrade Tableau Server, you should review and complete the Upgrade Checklist below and announce the expected downtime to users on the Tableau Enablement Intranet as shown in Tableau Communications. Specific tasks related to pre-TSM to TSM version upgrades are designated with an asterisk.
RESEARCH THE UPGRADE | YES | NO | N/A | Notes
Release Notes
What's New and Changed in Tableau Server
Upgrade from Tableau Server 2018.1 or earlier to TSM*
Comparing Functionality of tabadmin to TSM*
Upgrade process changes*
Validate sufficient capacity to support workload
Install on existing hardware
Migrate to New Hardware
Desktop and Server Compatibility
PREPARE FOR THE UPGRADE | YES | NO | N/A | Notes
Review and validate documented settings in Tableau Server Architecture & Configuration Design Document
Customizations
SMTP configuration
SSL configuration and certificates
SAML configuration, certificates, and IdP metadata files
Kerberos configuration
OpenID configuration
Addition node(s) configuration
Quantify projects, workbooks, views, data sources
Quantify users and groups
Download setup files for the new Tableau Server version
Back up Tableau Server data
Check your product maintenance status
TEST THE UPGRADE | YES | NO | N/A | Notes
Prepare a test environment
Upgrade the test environment
Confirm Tableau Server functionality
Server processes
User access
Publishing workbooks and data sources
View published workbooks
Subscriptions and extract refreshes
Permissions
Command-line utilities and APIs
Performance and user acceptance testing
Performance Resources
Test Workbook Performance
Test new features
Communicate the planned upgrade window
PERFORM THE SERVER UPGRADE | YES | NO | N/A | Notes
Communicate the pending upgrade
Disable subscriptions and scheduling
Create a pre-upgrade backup of Tableau Server data
Uninstall existing pre-TSM version of Tableau Server and save tsbak file to another location*
Upgrade Tableau Server (Existing TSM version) or Upgrade from Tableau Server 2018.1 or earlier to Tableau Server with TSM (Note: Gather existing files section*)
Install initial node
Install other nodes in cluster
Run the upgrade script to complete install
Login to TSM and start Tableau Server
Restore gathered files*
Validate the upgrade
Verify status of Tableau Server processes
Verify Tableau Server settings
Enable subscriptions and scheduling
Modify Tableau Server processes (if needed)
Review User access
Review User access
Verify publishing workbooks, data sources
View published workbooks
Review Permissions
Verify Command-line utilities and APIs
Login to Tableau Server
Verify count of projects, workbooks, views, data sources
Verify count of users and groups
Verify database connectivity
Execute backup script
Upgrade Resource Monitoring Tool and agents
Communicate the successful upgrade
PERFORM THE CLIENT UPGRADES | YES | NO | N/A | Notes
Communicate the pending upgrade
Upgrade Tableau Desktop
Upgrade Tableau Prep Builder
Upgrade tabcmd
Upgrade Content Migration Tool
Publish Tableau Mobile to MDM
Upgrade Tableau Bridge (for Tableau Online)

## Capacity Plan (hidden)
Capacity Plan
Purpose: Identify growth over time and maintain an 18-month outlook. To be completed by IT; aggregating use case/user data collected.
| Initial Deployment-6 months | 6-months-12 months | 12-months-18 months | 18-months-24 months
Users | 2000 | 4500 | 6500 | 10000
Cores
RAM
Note on C4: Michael Hetrick: Audience size collected from Use Cases
Note on D4: Michael Hetrick: Audience size collected from Use Cases
Note on E4: Michael Hetrick: Audience size collected from Use Cases
Note on F4: Michael Hetrick: Audience size collected from Use Cases